## Phase Overview
StockPredict — Chart Roadmap v2
Phases 1–6 ¦ Focus: StockChart.js ¦ As of 2026-05-24
Phase | Name | Key Deliverables | Primary File(s) | Effort | Status | Notes
Phase 1 | Foundation ✅ | • Responsive width (ResizeObserver) • MACD pane (replaces Elder Ray) • RSI overlay on price pane — right Y-axis • Indicator toggle dropdown (6 checkboxes) • Volume pane at bottom | StockChart.js | L | Done | Completed 2026-05-24. All 4 panes in one ChartCanvas.
Phase 2 | Overlay Indicators ✅ | • Bollinger Bands (upper/mid/lower on price pane) • VWAP line on price pane • Custom-period SMA selector • Add 3 new items to dropdown | StockChart.js chartTheme.js | M | Done | Completed 2026-05-25. BB, VWAP, custom-period SMA — all on price pane.
Phase 3 | More Oscillators ✅ | • Stochastic Oscillator (%K, %D) — new pane • ATR (Average True Range) — new pane • Pane height adjusts dynamically when toggled • Add to dropdown | StockChart.js | M | Done | Completed 2026-05-25. Stochastic (12,3,3) and ATR (14) panes; paneConfig refactor — sub-pane origins computed from SUB_PANE_HEIGHTS + enabled flags. Bottom-most enabled sub-pane shows date tick labels.
Phase 4 | Interactive Drawing Tools ✅ | • Trend line (click-drag) • Horizontal support/resistance line • Fibonacci retracement tool • Toolbar to select draw mode / clear all | StockChart.js DrawingToolbar.js (new) | L | Done | Completed 2026-05-25. TrendLine + InteractiveYCoordinate (H-line) + FibonacciRetracement wired into price pane. DrawingToolbar in header. Per-symbol persistence in localStorage. Clear-all action; per-item delete only on H-line.
Phase 5 | Chart Enhancements ✅ | • Timeframe tabs: 1M / 3M / 6M / 1Y / All • Candlestick type toggle: Candle / Heikin-Ashi / OHLC Bar • Save indicator preferences to localStorage • Crosshair tooltip showing all active values | StockChart.js AIInsights.js TechnicalAnalysis.js | M | Done | Completed 2026-05-25. Timeframe tabs (1M/3M/6M/1Y/All), candle/Heikin-Ashi/OHLC-bar toggle, localStorage per-symbol prefs, HoverTooltip with all active values.
Phase 6 | Multi-stock Comparison (Future) | • Overlay a second stock as a % return line • Colour-coded legend • Comparator symbol picker | StockChart.js | XL | Not Started | Lower priority — requires normalising two price series to % return from start date.
Effort key: | S = < 2 h | M = 2–4 h | L = 4–8 h | XL = > 8 h

## Chart Tasks
Chart Tasks — Detailed
ID | Phase | Task | Component / File | API / Symbol | Effort | Status | Depends On | Notes
C-101 | 1 ✅ | Responsive chart width via ResizeObserver | StockChart.js | useRef, ResizeObserver | S | Done |  | containerRef + useState(chartWidth)
C-102 | 1 ✅ | Replace Elder Ray pane with MACD pane | StockChart.js | macd(), MACDSeries, MACDTooltip | S | Done |  | fast=12 slow=26 signal=9; MACD_APPEARANCE constant
C-103 | 1 ✅ | RSI (14) overlay on price pane, right Y-axis | StockChart.js | rsi(), RSISeries, RSITooltip | S | Done |  | Chart id=2 at origin=[0,0] yExtents=[0,100]; axisAt=right
C-104 | 1 ✅ | Indicator toggle dropdown (6 checkboxes) | StockChart.js | useState(indicators), ResizeObserver | M | Done |  | Dropdown closes on outside click; pane heights shrink dynamically
C-105 | 1 ✅ | Dynamic canvas height when panes toggled | StockChart.js | macdHeight/volHeight conditional | S | Done | C-104 | Height = priceH + macdH + volH; recalc on each render
C-201 | 2 ✅ | Bollinger Bands on price pane | StockChart.js | bollingerBand(), BollingerSeries | S | Done |  | Upper/mid/lower LineSeries; add 'BB (20,2)' checkbox
C-202 | 2 ✅ | VWAP line on price pane | StockChart.js | No built-in — compute manually | M | Done |  | VWAP = cumSum(price*vol)/cumSum(vol); reset daily; draw as LineSeries
C-203 | 2 ✅ | Custom SMA period input | StockChart.js | sma(), LineSeries | S | Done |  | Small number input in dropdown alongside SMA checkbox; default period 20
C-204 | 2 ✅ | Add Phase 2 indicators to dropdown | StockChart.js | INDICATOR_OPTIONS array | S | Done | C-201,C-202,C-203 | Append BB, VWAP, SMA to INDICATOR_OPTIONS; same toggle pattern
C-301 | 3 ✅ | Stochastic Oscillator pane (%K / %D) | StockChart.js | stochasticOscillator(), StoSeries | M | Done |  | Separate pane; reference lines at 20/80; add to dropdown
C-302 | 3 ✅ | ATR (Average True Range) pane | StockChart.js | atr(), AreaOnlySeries or LineSeries | S | Done |  | Separate pane; no fixed scale — yExtents auto; shows volatility
C-303 | 3 ✅ | Pane ordering & height config object | StockChart.js | paneConfig array | M | Done | C-301,C-302 | Refactor hardcoded heights into a paneConfig[] so new panes slot in cleanly
C-401 | 4 ✅ | Trend line drawing tool | StockChart.js DrawingToolbar.js | TrendLine (interactive pkg) | M | Done |  | react-financial-charts/interactive; state array of drawn lines
C-402 | 4 ✅ | Horizontal S/R line tool | StockChart.js | GannFan or StraightLine interactive | S | Done | C-401 | Click to place; drag to move; right-click to delete
C-403 | 4 ✅ | Fibonacci retracement tool | StockChart.js | FibonacciRetracement (interactive) | M | Done | C-401 | Click high → drag to low; auto-draws 23.6 / 38.2 / 50 / 61.8 levels
C-404 | 4 ✅ | Drawing toolbar UI | DrawingToolbar.js (new) | React state: activeTool | M | Done | C-401,C-402,C-403 | Icon buttons: cursor / trend / H-line / Fib / eraser; highlighted when active
C-501 | 5 ✅ | Timeframe selector tabs (1M/3M/6M/1Y/All) | AIInsights.js TechnicalAnalysis.js | slice(data, -N) | S | Done |  | xExtents clipped server-side or client-side slice; pass as prop or internal state
C-502 | 5 ✅ | Candlestick type toggle (Candle/Heikin-Ashi/Bar) | StockChart.js | heikinAshi(), CandlestickSeries, OHLCSeries | M | Done |  | heikinAshi() calc transforms OHLC; swap series component based on toggle
C-503 | 5 ✅ | Persist indicator prefs in localStorage | StockChart.js | localStorage.getItem/setItem | S | Done | C-104 | Key: `stockchart_indicators_${symbol}`; load on mount, save on change
C-504 | 5 ✅ | Unified crosshair tooltip (all values) | StockChart.js | OHLCTooltip + custom SVG tooltip | M | Done |  | Custom tooltip component overlaying OHLC, EMA12/26, RSI, MACD at cursor position
C-601 | 6 | Second-stock % return overlay | StockChart.js | compare() indicator | XL | Not Started |  | Normalise both series to 100 at start date; LineSeries on right axis
C-602 | 6 | Comparator symbol picker UI | StockChart.js | ComparatorSelector component | M | Not Started | C-601 | Dropdown to pick comparison ticker; shows coloured legend

## Session Log
Session Log
Date | Phase(s) Touched | Tasks Completed | Files Changed | Where I Left Off | Next Session Start
2026-05-24 | Phase 1 | C-101 Responsive width C-102 MACD pane C-103 RSI overlay right-axis C-104 Indicator dropdown C-105 Dynamic canvas height | StockChart.js nginx.conf (cache fix) Sidebar.js / MainLayout.js (Decision Helper Overview) en.json / vi.json | All Phase 1 chart tasks done. Frontend rebuilt & deployed to Docker (port 3004). nginx cache-control fix committed. | Start Phase 2: Bollinger Bands (C-201) → import bollingerBand from react-financial-charts → add BollingerSeries to price Chart (id=1) → add 'BB (20,2)' to INDICATOR_OPTIONS
2026-05-25 | Phase 2 | C-201 Bollinger Bands (20,2) C-202 VWAP (anchored cumulative) C-203 Custom-period SMA + number input C-204 Extended INDICATOR_OPTIONS | StockChart.js roadmap_version_2.xlsx | Phase 2 done. Production build clean (only pre-existing ESLint warnings in unrelated files). New indicators default OFF to avoid initial clutter. BB tooltip at origin [8,40]; SMA period input in dropdown (clamped 2–200). | Phase 3: Stochastic Oscillator pane (C-301), ATR pane (C-302), paneConfig refactor (C-303). Tip: refactor hardcoded pane heights into a paneConfig[] array first — Phase 3 introduces 2 new panes.
2026-05-25 | Phase 3 | C-303 paneConfig refactor (SUB_PANE_HEIGHTS + paneOrigin lookup) C-301 Stochastic Oscillator pane (12,3,3) with %K/%D + tooltip C-302 ATR (14) pane — LineSeries + SingleValueTooltip | StockChart.js roadmap_version_2.xlsx | Phase 3 done. Same session as Phase 2. Refactor first: hardcoded macdHeight/volHeight replaced with SUB_PANE_HEIGHTS={macd,stoch,atr,volume} and computed paneOrigin. Bottom-most enabled sub-pane now owns the date tick labels + MouseCoordinateX (previously only volume showed them). Stochastic and ATR default OFF. Production build clean (+771 B gzipped). | Phase 4: Drawing tools — trend line (C-401), horizontal S/R (C-402), Fibonacci (C-403), drawing toolbar UI (C-404). Requires @react-financial-charts/interactive (already bundled in v2). New DrawingToolbar.js component + persisted drawings array state.
2026-05-25 | Phase 5 | C-501 Timeframe tabs (1M/3M/6M/1Y/All) — internal slice C-502 Candle / Heikin-Ashi / OHLC Bar toggle (HA computed manually into haOpen/haHigh/haLow/haClose so candles toggle non- destructively and indicators keep using real OHLC) C-503 Per-symbol localStorage prefs (indicators, smaPeriod, timeframe, candleType) keyed by stockchart_prefs_{symbol} C-504 HoverTooltip on price pane — OHLC + all active indicators | StockChart.js CompanyCharts.js (pass symbol prop) roadmap_version_2.xlsx | Phase 5 done. Same session as Phases 2 + 3. When a timeframe other than "All" is selected, the initial x-window fits the whole sliced range (not the legacy 100-row window). CompanyCharts already had outer 1W/1M/1Y/5Y buttons — left in place; inner tabs further slice whatever the parent passes. Slight duplication but no regression. Cleanup is a UX task for later. Bundle: +2.84 kB gzipped. | Phase 4: Drawing tools. Imports from @react-financial-charts/interactive: TrendLine, EquidistantChannel/StraightLine for H-line, FibonacciRetracement, plus new DrawingToolbar.js component. Decisions to make on entry: • toolbar position (left rail vs. top-right next to dropdown) • drawings persistence: state-only vs. localStorage per symbol • default active tool: cursor (recommended)
2026-05-25 | Phase 4 | C-404 New DrawingToolbar.js with cursor/trend/hline/fib + Clear-all C-401 TrendLine wired with state-driven trends[] array C-402 InteractiveYCoordinate for horizontal S/R lines: onChoosePosition adds, onDragComplete moves, onDelete removes C-403 FibonacciRetracement (BOUND type) wired with retracements[] Drawings persisted per symbol under stockchart_drawings_{symbol} | StockChart.js DrawingToolbar.js (new) roadmap_version_2.xlsx | Phase 4 done. Same session as Phases 2 + 3 + 5. Toolbar position: top-left next to timeframe/candle tabs. Default tool: cursor (chart starts in pan/zoom mode). Per-item delete: only H-line via onDelete callback. Trend/Fib rely on Clear-all (DrawingObjectSelector wiring is a future polish). Bundle: +7.78 kB gzipped (interactive package is the heavyweight). | All planned phases (1–5) now Done. Phase 6 (Multi-stock comparison) remains Not Started — XL effort, flagged future in the roadmap. Polish backlog: • DrawingObjectSelector + DEL key for per-item delete • Snap-to-bar option for trend lines (snap={true}+snapTo) • Remove the legacy bootstrap buttons in CompanyCharts (now redundant with the internal timeframe tabs) • Clean up stub Select for "Leanne Graham" / "Ervin Howell"
2026-05-25 | Cleanup | Removed legacy bootstrap buttons (1w/1m/1y/5y/All) + stub react-dropdown-select ("Leanne Graham") from CompanyCharts.js. Now redundant after Phase 5 internal timeframe tabs in StockChart. Also dropped: periodStockData slicing state, debug console.log, unused selectItem/styles/options. | CompanyCharts.js | Browser-verified Phases 2–5 working end-to-end on port 3004 (user signed off: "beautiful charts"). Cleanup: −105 / +26 lines in CompanyCharts.js. Bundle: −18 kB gzipped (vs. Phase 4 commit) — bootstrap CSS was being imported via this file. react-bootstrap stays as a dependency since Solutions/TimeSeries/Agent pages still use it. | Polish backlog remaining: • DrawingObjectSelector + DEL key for per-item drawing delete • Snap-to-bar option for trend lines (snap={true}+snapTo) • Misleading "demo / password" hint on login screen (server rejects with 422 — email field validated as email) • Transient <rect> negative-height SVG warning at chart init • Phase 6 (multi-stock compare) — XL, still Not Started
2026-05-25 | Cleanup | Removed misleading "Demo account: demo/password" hint from LoginForm. | LoginForm.js auth.css en.json / vi.json | Hint was broken: auth-service validates the username field as an email and rejected "demo" with 422. No demo user was seeded. Removed JSX block, .auth-demo / .auth-demo-text CSS rules, and login.demo_account translation keys in both locales. Bundle: −92 B gzipped (JS), −41 B (CSS). | Polish backlog still open: • DrawingObjectSelector + DEL key for per-item drawing delete • Snap-to-bar for trend lines • Transient <rect> negative-height SVG warning at chart init • Phase 6 (multi-stock compare)

## API Reference
react-financial-charts v2 — Indicators Quick Reference
Indicator | Calculator Import | Series Component | Tooltip | Notes
EMA | ema() | LineSeries | MovingAverageTooltip | Done ✅
SAR | sar() | SARSeries | — | Done ✅
MACD | macd() | MACDSeries | MACDTooltip | Done ✅ Need appearance prop
RSI | rsi() | RSISeries | RSITooltip | Done ✅ Need displayFormat prop
Bollinger Bands | bollingerBand() | BollingerSeries | BollingerBandTooltip | Phase 2
SMA | sma() | LineSeries | MovingAverageTooltip | Phase 2
Stochastic | stochasticOscillator() | StochasticSeries | StochasticTooltip | Phase 3 — check exact export name
ATR | atr() | AreaOnlySeries | SingleValueTooltip | Phase 3
Heikin-Ashi | heikinAshi() | CandlestickSeries | OHLCTooltip | Phase 5 — transforms OHLC data
VWAP | manual (no built-in) | LineSeries | SingleValueTooltip | Phase 2 — compute in data layer
Trend Line | — | TrendLine | — | Phase 4 — from interactive package
Fibonacci | — | FibonacciRetracement | — | Phase 4 — from interactive package