## Overview
StockPredict — Road Map v11: Trader Decision Helper
Plan for a new feature that helps traders decide WHEN to take an opportunity, WHEN to cut a loss, and HOW to size the position — operationalising Schwager's 'Getting Started in Technical Analysis'.
What this is
Goal | Give the trader, for any watched ticker on any bar, a single recommendation (BUY / SELL / HOLD / WAIT / REVERSE) plus a stop, a target, and a position size — all justified by an auditable chain of indicators, patterns, regime, and confirmation rules drawn from Schwager.
Non-goal (v1) | We do NOT auto-execute orders. The helper recommends; the trader (or the broker integration in a later phase) acts. Paper-trading + journal-loop closes the feedback cycle.
Inputs | 1) Pipeline diagram: knowledge/stock_pipeline_v3.drawio 2) Book notes: knowledge/stock/books/getting-started-in-technical-analysis_compress.pdf/part_1..4/ 3) Existing stockpredict services (9 FastAPI services + React 19 frontend).
New service | decision-helper-service (port 8010). Orchestrates: regime -> signal -> confirm -> failed-signal check -> state-machine update -> recommendation + stop/target/size. Emits events to journal-service and portfolio-service.
Existing services to extend | analysis-service (add ATR, swing pivots, regime endpoint, midtrend-entry detectors); ai-insights-service (add H&S / double-top / flag-pennant / WRD / gaps / trap detectors); journal-service (auto-pre-fill draft entries from helper events); portfolio-service (sync stops + targets as alerts).
New frontend pages | DecisionConsole (per-symbol), WatchlistDecisionBoard (multi-symbol), TradePlanModal (gated entry — refuses to save without stop+target), BacktestStudio, DisciplineDashboard.
How to read this workbook | Pipeline_Mapping → see every drawio stage mapped to existing code and new modules. Architecture → components to build. Backlog → concrete tickets. Phased_Roadmap → order of attack. Book_Chapter_Map → which chapter informs which module. Risks_Open_Questions → what we need to clarify before coding.
Success criteria | 1) For 5 tickers on daily bars, helper produces a recommendation in < 2s. 2) Walk-forward backtest on 3+ non-overlapping periods shows positive expectancy after slippage. 3) Every entry recorded in journal includes auto-generated reason linked to the signal+regime that produced it. 4) Trader cannot save a trade plan without a stop and a target (Ch 16-17 discipline).
Out of scope (v1) | Intraday/tick data, order-execution integration with brokers, options/futures, automated portfolio rebalancing, multi-account.

## Pipeline_Mapping
Stage ID | Stage (drawio) | What it does | Current state in stockpredict | New module to build | Owner service | Book chapter(s) | Priority | Status
s1_universe | 1. Select 5 stock tickers | Pre-filter universe (fundamentals, liquidity) before technical analysis runs. | Watchlist + screener exist (portfolio-service, analysis-service) | Wire watchlist -> decision pipeline trigger; add liquidity filter helper. | portfolio-service + decision-helper-service | Ch 16 (market selection) | P1 (should) | Planned
s2_data | 2. Get historical OHLCV (daily) | Daily OHLCV per ticker; splits/dividend adjusted. | Exists in stock-data-service (vnstock) | Expose a clean daily-bars endpoint that includes adjusted close + volume. | stock-data-service | Ch 13 (data) | P0 (must) | Partial
s3_indicators | 3. Compute indicators | MAs, ATR, RSI/MACD/Stoch, swing pivots — every bar. | RSI, MACD, BB, SMA/EMA in analysis-service; ADX in prediction-service (ta-lib) | Add ATR endpoint, swing-pivot detector, consolidated indicator pack response. | analysis-service | Ch 3, 6 | P0 (must) | Partial
s4_patterns | 4. Detect chart patterns | Gaps, continuation, reversal, wide-range bar. | ai-insights-service: Uptrend/Downtrend/Consolidation/Breakout only | Extend pattern catalog: H&S, double top/bottom, flag, pennant, triangle, WRD, gaps, bull/bear traps. | ai-insights-service | Ch 5, 11, 12 | P0 (must) | In Progress
s5_regime | 5. Regime? (trend vs trading range) | Classify the bar as trending or ranging using MA slope, swing structure, ADX, range/ATR. | Nothing explicit — must build | regime_classifier module — outputs {trend, range, undefined} + confidence. | decision-helper-service | Ch 3, 4 | P0 (must) | Not Started
s6L_direction | 6L. Up or down trend? | Branch within trend regime: direction = long-bias or short-bias. | Inferred from SMA/EMA cross today | trend_direction helper using long-MA slope + swing structure. | decision-helper-service | Ch 3 | P0 (must) | Not Started
s6R_range | 6R. Trading range — locate S/R | Inside a range, find support floor and resistance ceiling. | analysis-service _find_support_resistance() (local minmax) | Promote S/R into a typed level object with strength/age; expose to decision helper. | analysis-service | Ch 4 | P0 (must) | Partial
s7L_signal | 8L. Trend-following signal | MA crossover or N-day breakout entry trigger. | Score-based signal in analysis-service _determine_signal() — not state-aware | signal_engine.trend: MA-cross, N-day breakout, midtrend pullback/retracement/flag. | decision-helper-service | Ch 8, 14 | P0 (must) | Not Started
s7R_breakout | 7R. Breakout? | Has the range broken out (price closed past S or R)? | Nothing explicit | breakout_detector with penetration + close-confirmation. | decision-helper-service | Ch 4, 14 | P0 (must) | Not Started
s9L_filter | 9L. Filter + confirmation (trend) | Direction filter, penetration, time delay before entering. | Nothing explicit | confirmation_layer: penetration N%, time-delay K bars, multi-TF alignment. | decision-helper-service | Ch 7, 14 | P0 (must) | Not Started
s8R_confirm | 8R. Confirm breakout direction | Penetration + time-delay confirmation for breakout entry. | Nothing explicit | confirmation_layer reused on breakout branch. | decision-helper-service | Ch 7, 14 | P0 (must) | Not Started
s10L_failed | 10L. Signal failed? -> consider reversal | Detect a failed trend signal; if yes, reverse (Schwager: most important rule). | Nothing exists | failed_signal_detector for trend branch: bull/bear trap, false trend-line break, filled gap, return to spike/WRD extreme. | decision-helper-service | Ch 11 | P0 (must) | Not Started
s9R_failed | 9R. Breakout failed? | Bull / bear trap detection on the range branch. | Nothing exists | failed_signal_detector reused on range branch. | decision-helper-service | Ch 11 | P0 (must) | Not Started
state_machine | Position state machine (FLAT / LONG / SHORT) | Per (user, ticker): current state + incoming signal -> next action. Pyramid self-loops (Ch 8) are deferred. | Portfolio tracks holdings only — no state-machine for active 'trade idea' | position_state_machine — DB-backed; transitions on confirmed signal, stop, target, or reversal. | decision-helper-service | Ch 8, 14 | P0 (must) | Not Started
out_actions | BUY / SELL / SELL short / COVER / HOLD / WAIT | Action emitted at each bar based on (state, signal). | Nothing exists | decision_orchestrator — outputs the action plus reason chain. | decision-helper-service | Ch 12, 14, 17 | P0 (must) | Not Started
log_loop | Log decision (action + reason + state) & advance bar | Persist what was decided and why; backtest replay-friendly. | Journal logs trades; no per-bar decision log | decision_runs table + Kafka/RabbitMQ event 'decision.recommendation.created'. | decision-helper-service | Ch 16 | P0 (must) | Not Started
risk_stops | Risk overlay: Stop-loss (Ch 9) | Initial + trailing stops anchored on ATR / swing / S/R / pattern boundary. | Portfolio price alerts only — no auto stop computation | stop_module: chart-based, swing, ATR, pattern, WRD, money-stop, trailing. Validation: never widen. | decision-helper-service + portfolio-service (sync as alert) | Ch 9, 17 | P0 (must) | Not Started
risk_sizing | Risk overlay: Position sizing (Ch 16) | Compute size from (account risk %, entry - stop). ATR-adjusted; equity-adjusted. | PositionCalculator.js UI exists but is not wired | sizing_module: fixed-fractional, vol-adjusted, equity-adjusted, correlation cap, losing-streak adjustment. | decision-helper-service | Ch 16 | P0 (must) | Not Started
risk_targets | Risk overlay: Profit targets (Ch 10) | S/R level, measured-move, partial exits + trailing take-profit. | portfolio-service has target_price field on alerts; nothing computes it | target_module: S/R objective, measured move, RSI extreme (range), trailing TP. | decision-helper-service + portfolio-service (sync) | Ch 10 | P0 (must) | Not Started
regime_inputs | Regime classifier inputs | Long-MA slope, swing high/low structure, range width vs ATR, ADX, pattern context. | ADX exists; swing structure does not | Aggregate features into a single 'regime feature vector'. | analysis-service -> decision-helper-service | Ch 3, 4 | P0 (must) | Not Started
osc_note | Oscillator-use rule (Ch 6) | In trend -> oscillators are alert-only. In range -> actionable at boundaries. | Score-based signal blends oscillators with price unconditionally | confirmation_layer applies this rule by branch (trend vs range). | decision-helper-service | Ch 6 | P1 (should) | Not Started
failed_signal_principle | Failed-signal principle (Ch 11) | Schwager's 'most important rule' — a failed pattern is itself a stronger signal. | Nothing exists | failed_signal_detector wires into BOTH branches and triggers reversal. | decision-helper-service | Ch 11, 17 (rule 76) | P0 (must) | Not Started
backtest_harness | Backtest / walk-forward (Ch 15) | Replay the pipeline on history with realistic slippage; out-of-sample evaluation. | prediction-service has simulation/backtest UI; no walk-forward for decision helper | backtest_harness reusing decision_orchestrator over historical bars; multi-period, multi-market. | decision-helper-service + prediction-service | Ch 15 | P1 (should) | Not Started
discipline | Discipline overlay (Ch 17, 82 rules) | Reject trade plans without stop+target; detect averaging-down, stop-widening, post-streak risk creep. | Journal captures emotional state; no enforcement layer | discipline_checks module + TradePlanModal gate + DisciplineDashboard. | decision-helper-service + journal-service + frontend | Ch 16, 17 | P1 (should) | Not Started

## Architecture
Component | Type | Location (proposed) | Purpose | Depends on | Book chapters | Status
decision-helper-service | Service (new) | stock_microservices/services/decision-helper-service/ | Orchestrates the full pipeline; emits recommendation per (user, ticker, bar). FastAPI on port 8010. | stock-data-service, analysis-service, ai-insights-service, journal-service, portfolio-service, MySQL, Redis, RabbitMQ | All | Not Started
regime_classifier | Module | .../app/services/regime_classifier.py | Classifies bar as TREND / RANGE / UNDEFINED using MA slope, swing structure, ADX, range/ATR. | indicators pack, swing pivots | Ch 3, 4 | Not Started
signal_engine | Module | .../app/services/signal_engine/ | Submodules: trend (MA cross, N-day breakout, midtrend), range (S/R bounce, breakout), countertrend (osc fade). | regime_classifier, indicators | Ch 6, 8, 14 | Not Started
confirmation_layer | Module | .../app/services/confirmation.py | Penetration %, time delay K bars, multi-TF alignment, oscillator-as-alert rule. | signal_engine output | Ch 7, 14 | Not Started
failed_signal_detector | Module | .../app/services/failed_signal.py | 12 detectors from Ch 11 (bull/bear trap, false TL break, filled gap, etc.). Triggers reversal. | patterns, signals, state_machine | Ch 11 | Not Started
stop_module | Module | .../app/services/stop_module.py | Chart-based, swing, ATR, pattern, WRD, money-stop, trailing. Validation: stops never widen. | indicators, patterns, state_machine | Ch 9 | Not Started
target_module | Module | .../app/services/target_module.py | S/R objective, measured move, RSI extreme (range), trailing TP. Partial exit support. | patterns, S/R levels | Ch 10 | Not Started
sizing_module | Module | .../app/services/sizing_module.py | Fixed-fractional, ATR-adjusted, equity-adjusted, correlation cap, losing-streak adjustment. | stop_module, account state, position correlations | Ch 16 | Not Started
position_state_machine | Module | .../app/services/state_machine.py | Per (user, ticker): FLAT / LONG / SHORT. Persists transitions; emits events. | decision_orchestrator | Ch 8, 14 | Not Started
decision_orchestrator | Module | .../app/services/orchestrator.py | Runs the pipeline for one bar of one ticker. Returns recommendation + reason chain. | everything above | Ch 12, 14 | Not Started
discipline_checks | Module | .../app/services/discipline.py | Plan-before-trade enforcement; no-averaging-down; stop-widening detector; streak detectors. | journal data, account history | Ch 16, 17 | Not Started
backtest_harness | Module | .../app/services/backtest.py | Walk-forward replay of orchestrator over historical bars; slippage; out-of-sample report. | decision_orchestrator, historical OHLCV | Ch 15 | Not Started
decision_runs (table) | DB table | MySQL `stockpredict`.decision_runs | One row per (user, ticker, bar): regime, signal, confirmation, recommendation, reason_json, stop, target, size, state_before, state_after. | MySQL | All | Not Started
position_states (table) | DB table | MySQL `stockpredict`.position_states | Current state per (user, ticker): state, entry_bar, entry_price, current_stop, current_target, size. | MySQL | Ch 8, 14 | Not Started
signal_history (table) | DB table | MySQL `stockpredict`.signal_history | Append-only log of raw signals (pre-confirmation) for analysis and backtest replay. | MySQL | Ch 15 | Not Started
user_risk_prefs (table) | DB table | MySQL `stockpredict`.user_risk_prefs | Per-user: risk_per_trade_pct, max_concurrent_positions, max_correlation, account_equity_snapshot. | MySQL, auth-service | Ch 16 | Not Started
decision.recommendation.created | Event | RabbitMQ /stock | Published every time a new recommendation is emitted; consumed by frontend (WebSocket) and journal-service (draft entry). | RabbitMQ | Ch 16 | Not Started
decision.signal.failed | Event | RabbitMQ /stock | Published when a signal turns into a failed-signal reversal candidate. | RabbitMQ | Ch 11 | Not Started
decision.stop.triggered / decision.target.hit | Event | RabbitMQ /stock | Published when a tracked position hits its stop or target. Consumed by journal-service and portfolio-service. | RabbitMQ | Ch 9, 10 | Not Started
analysis-service: ATR + swings | Extension | stock_microservices/services/analysis-service/app/services/analysis_service.py | Add _calculate_atr(), _find_swing_pivots(), and a /analysis/regime/{symbol} endpoint. | OHLCV | Ch 3, 9 | Not Started
ai-insights-service: pattern v2 | Extension | stock_microservices/services/ai-insights-service/app/services/insights_service.py | Add H&S, double top/bottom, flag, pennant, triangle, gap, WRD, bull/bear trap detectors. | OHLCV | Ch 5, 11, 12 | In Progress
journal-service: auto-draft | Extension | stock_microservices/services/journal-service/app/services/diary_service.py | Subscribe to decision events; create draft journal entries pre-filled with reason / stop / target / size. Trader confirms or edits. | RabbitMQ, decision-helper-service | Ch 16 | Not Started
portfolio-service: sync alerts | Extension | stock_microservices/services/portfolio-service/app/services/portfolio_service.py | When recommendation produces a stop/target, materialise as a portfolio alert automatically; cancel when state transitions. | RabbitMQ | Ch 9, 10 | Not Started
DecisionConsole | Frontend page | stock_react_javascript/stock-react-app/src/components/Pages/DecisionConsole/ | Per-symbol: chart + regime ribbon + signal card + recommendation + stop/target/size + reason chain. | decision-helper-service API | Ch 12 | Not Started
WatchlistDecisionBoard | Frontend page | .../components/Pages/WatchlistDecisionBoard/ | Multi-symbol table: regime, signal, recommendation, change since last bar. Sortable/filterable. | decision-helper-service API | Ch 16 | Not Started
TradePlanModal | Frontend component | .../components/Common/TradePlanModal.js | Gated entry: cannot save a planned trade without stop + target. Pre-fills from recommendation. | journal-service, decision-helper-service | Ch 9, 16, 17 | Not Started
BacktestStudio | Frontend page | .../components/Pages/BacktestStudio/ | Walk-forward UI: pick periods + markets + parameter sets, view OOS expectancy, drawdown, win rate. | decision-helper-service /backtest API | Ch 15 | Not Started
DisciplineDashboard | Frontend page | .../components/Pages/DisciplineDashboard/ | Streaks, drawdown, rule-violation log, post-loss break suggestion. | discipline_checks API, journal-service | Ch 16, 17 | Not Started

## Feature_Backlog
ID | Phase | Area | Feature | Description / Acceptance criteria | Chapter(s) | Effort | Priority | Depends on | Status
F-001 | A | analysis-service | Add ATR indicator | Implement _calculate_atr(period=14). Expose at /analysis/atr/{symbol}. AC: returns 14-bar ATR aligned with OHLCV index; unit test on 2 known series. | Ch 9 | S | P0 (must) | — | Not Started
F-002 | A | analysis-service | Add swing-pivot detector | Detect higher highs / lower lows over rolling window K. Expose at /analysis/swings/{symbol}. AC: returns list of (bar_index, type, price); deterministic across reruns. | Ch 3 | M | P0 (must) | — | Not Started
F-003 | A | analysis-service | Promote S/R levels to typed objects | Refactor _find_support_resistance() to return {price, strength, age_bars, touches}. AC: backwards-compatible response; new fields populated. | Ch 4 | S | P0 (must) | F-002 | Not Started
F-004 | A | analysis-service | Regime feature vector endpoint | /analysis/regime/{symbol} -> {regime, confidence, features:{slope, hh_hl_count, adx, range_atr_ratio}}. | Ch 3, 4 | M | P0 (must) | F-001, F-002 | Not Started
F-005 | A | ai-insights-service | Extend pattern catalog | Add detectors: H&S, double top/bottom, flag, pennant, triangle, gap, wide-ranging day. AC: each returns {found, confidence, key_bars, measured_move_target}. | Ch 5, 12 | L | P0 (must) | F-002 | In Progress (Day 1/3 — reversal patterns done)
F-006 | A | ai-insights-service | Bull / bear trap detector | Detect penetration of S/R that closes back inside range within N bars. AC: returns trap event with severity. | Ch 11 | M | P0 (must) | F-003, F-005 | Not Started
F-010 | B | decision-helper-service | Bootstrap FastAPI service (port 8010) | Stand up service with health probe, DB migrations baseline, Traefik route /helper/*. AC: deploy.sh starts it; GET /health 200. | — | S | P0 (must) | — | Not Started
F-011 | B | decision-helper-service | DB schema: decision_runs, position_states, signal_history, user_risk_prefs | Alembic migration with the four tables described in Architecture sheet. | — | M | P0 (must) | F-010 | Not Started
F-012 | B | decision-helper-service | regime_classifier module | Pull regime features from analysis-service; output {trend, range, undefined} + confidence. AC: unit test on synthetic trending vs ranging series. | Ch 3, 4 | M | P0 (must) | F-004, F-010 | Not Started
F-013 | B | decision-helper-service | signal_engine.trend.ma_cross | MA-crossover detector with configurable fast/slow periods. AC: emits BUY/SELL signal at crossover bar. | Ch 14 | S | P0 (must) | F-010 | Not Started
F-014 | B | decision-helper-service | signal_engine.trend.n_day_breakout | N-day high/low breakout detector. AC: configurable N; long signal on close > N-day high. | Ch 14 | S | P0 (must) | F-010 | Not Started
F-015 | B | decision-helper-service | signal_engine.range.sr_bounce_breakout | Inside a range: bounce signal at support/resistance; breakout signal on close past S/R. | Ch 4, 14 | M | P0 (must) | F-003 | Not Started
F-016 | B | decision-helper-service | confirmation_layer | Penetration % + time-delay K + multi-TF alignment + oscillator-as-alert rule. Configurable thresholds. AC: confirms/rejects each raw signal with reason. | Ch 7, 14 | M | P0 (must) | F-013, F-014, F-015 | Not Started
F-020 | C | decision-helper-service | stop_module — chart / swing / ATR / pattern | Compute initial stop per entry type. Validation: stop never widens after entry (unit test the CIC anti-pattern). | Ch 9 | L | P0 (must) | F-001, F-002, F-003 | Not Started
F-021 | C | decision-helper-service | stop_module — trailing stop | Update stop on each new favorable bar; never relax. | Ch 9, 10 | M | P0 (must) | F-020 | Not Started
F-022 | C | decision-helper-service | target_module — S/R + measured move | Pick first viable target from S/R level or measured move from pattern. | Ch 10 | M | P0 (must) | F-003, F-005 | Not Started
F-023 | C | decision-helper-service | target_module — partial exits | Support 50% at first target + trailing on remainder. | Ch 10 | M | P1 (should) | F-022 | Not Started
F-024 | C | decision-helper-service | sizing_module v1 (fixed-fractional) | size = floor(risk_pct * equity / (entry - stop)). AC: rejects size < 1. | Ch 16 | S | P0 (must) | F-020 | Not Started
F-025 | C | decision-helper-service | sizing_module v2 (ATR + equity + correlation + streak) | ATR-adjustment, equity-adjustment, correlation cap, losing-streak halving. | Ch 16 | L | P1 (should) | F-024 | Not Started
F-026 | C | decision-helper-service | position_state_machine | FLAT/LONG/SHORT transitions; persists to position_states. AC: cannot transition LONG->SHORT without passing through FLAT (v1). | Ch 8, 14 | M | P0 (must) | F-011 | Not Started
F-027 | C | decision-helper-service | decision_orchestrator | Run one bar of one ticker through the pipeline; return recommendation + reason chain; persist to decision_runs. | Ch 12, 14 | L | P0 (must) | F-012..F-026 | Not Started
F-030 | D | frontend | API client + decision context | Add helperApi.js; React context for current symbol's latest recommendation. | — | S | P0 (must) | F-027 | Not Started
F-031 | D | frontend | DecisionConsole page | Per-symbol: chart, regime ribbon, signal card, recommendation, stop/target/size, reason chain. Manual test on 3 tickers in browser. | Ch 12 | L | P0 (must) | F-030 | Not Started
F-032 | D | frontend | WatchlistDecisionBoard | Multi-symbol table of recommendations; sort by signal-change-since-last-bar. | Ch 16 | M | P0 (must) | F-031 | Not Started
F-033 | D | frontend | TradePlanModal (gated) | Cannot save plan without stop + target; pre-fills from recommendation. Wires to journal-service. | Ch 9, 16, 17 | M | P0 (must) | F-031 | Not Started
F-034 | D | journal-service | Auto-draft journal entry from decision event | Subscribe to decision.recommendation.created; create draft entry with reason chain. | Ch 16 | M | P1 (should) | F-027 | Not Started
F-035 | D | portfolio-service | Sync stops + targets as portfolio alerts | When recommendation has a stop/target, create matching alert. Cancel on state exit. | Ch 9, 10 | M | P1 (should) | F-027 | Not Started
F-040 | E | decision-helper-service | failed_signal_detector — 12 detectors | Implement each Ch-11 type as boolean + parameters (bull/bear trap, false TL break, filled gap, return to spike, WRD return, counter-anticipated flag, opposite breakout, H&S target failure, double-top break, rounding break, future-reliability tag). | Ch 11 | L | P0 (must) | F-005, F-006 | Not Started
F-041 | E | decision-helper-service | Reversal action wiring | When detector fires, orchestrator emits REVERSE; state-machine flips LONG<->SHORT via FLAT. | Ch 11, 17 | M | P0 (must) | F-040, F-026 | Not Started
F-042 | E | decision-helper-service | signal_engine.midtrend | Four midtrend entries: % retracement, minor-reaction reversal, continuation breakout, long-MA reaction. | Ch 8 | L | P1 (should) | F-027 | Not Started
F-043 | E | decision-helper-service | Pyramiding (deferred guard rails) | Allow additive entries to a winning position with 3 risk guards: max 50% from pyramids, tighter stops on add, no-add after N consecutive losses. | Ch 8, 14 | L | P2 (could) | F-042, F-025 | Not Started
F-050 | F | decision-helper-service | backtest_harness — replay engine | Run orchestrator over historical bars; produce trade ledger + equity curve. | Ch 15 | L | P1 (should) | F-027 | Not Started
F-051 | F | decision-helper-service | Walk-forward train/test split | Non-overlapping windows; optimise on train, evaluate on test; aggregate across windows. | Ch 15 | L | P1 (should) | F-050 | Not Started
F-052 | F | decision-helper-service | Slippage + commissions model | Configurable bps slippage and per-trade commission; applied in backtest. | Ch 15 | S | P1 (should) | F-050 | Not Started
F-053 | F | decision-helper-service | Parameter-set sensitivity report | Run 5+ neighboring parameter sets; report variance — flag fragile optima. | Ch 15 | M | P2 (could) | F-051 | Not Started
F-054 | F | frontend | BacktestStudio page | UI for parameter sets / periods / markets; render equity curve + drawdown + win rate. | Ch 15 | L | P2 (could) | F-051 | Not Started
F-060 | G | decision-helper-service | discipline_checks — plan-before-trade | Block any TradePlanModal save where stop or target is missing. | Ch 16, 17 | S | P1 (should) | F-033 | Not Started
F-061 | G | decision-helper-service | discipline_checks — no averaging down | Detect when an open losing position receives a new entry signal in the same direction; warn / require override. | Ch 17 (rule 14) | M | P1 (should) | F-026 | Not Started
F-062 | G | decision-helper-service | discipline_checks — stop-widening detector | Warn whenever user-edited stop is wider than current orchestrator stop. | Ch 9, 17 | S | P1 (should) | F-020 | Not Started
F-063 | G | decision-helper-service | Streak detectors + post-loss break | Detect N consecutive losses or > 20% drawdown; trigger size reduction; suggest break. | Ch 16, 17 | M | P2 (could) | F-025 | Not Started
F-064 | G | frontend | DisciplineDashboard | Streaks, drawdown, rule-violation log, last-N-trades summary. | Ch 16, 17 | M | P2 (could) | F-060..F-063 | Not Started
F-065 | G | all | Schwager 82-rules engine (advisory) | Codify rules from Ch 17 as advisory checks surfaced in DecisionConsole sidebar. | Ch 17 | L | P2 (could) | F-031 | Not Started

## Phased_Roadmap
Phase | Name | Goal | Key deliverables | Exit criteria | Est. weeks | Depends on | Status
A | Foundations: indicators + patterns + regime features | Make the inputs the decision pipeline needs available from existing services. | ATR + swing pivots (analysis-service); S/R typed levels; regime feature endpoint; extended pattern catalog + bull/bear trap detector (ai-insights-service). | All Phase-A backlog (F-001..F-006) green. Decision service can fetch every feature it needs from existing services with one HTTP call per type. | 2 | — | Not Started
B | decision-helper-service skeleton + signal engine v1 | Stand up the new service; ship trend-following + range signal generators with a confirmation layer. | Service bootstrap, DB schema, regime_classifier, signal_engine (MA cross, N-day breakout, S/R bounce / breakout), confirmation_layer. | F-010..F-016 green. End-to-end: given (user, ticker, bar) the service emits a confirmed raw signal with a reason payload. | 3 | A | Not Started
C | Risk overlay + state machine + orchestrator | Wrap signals with stop / target / size and a persistent FLAT/LONG/SHORT state machine. | stop_module, target_module, sizing_module v1, position_state_machine, decision_orchestrator. | F-020..F-027 green. Orchestrator returns a full recommendation (action + stop + target + size + reason) stored in decision_runs. Replay on 5 tickers, 1 year of bars completes < 30s. | 3 | B | Not Started
D | Frontend MVP: DecisionConsole + Watchlist + TradePlan + journal/portfolio wiring | Make the helper usable by a real trader; close the loop with journal and portfolio alerts. | DecisionConsole, WatchlistDecisionBoard, TradePlanModal (gated), journal auto-draft, portfolio alert sync. | Trader can review 5 watched tickers, accept a recommendation, save a plan (with stop+target enforced), and see the corresponding journal draft + portfolio alert. | 3 | C | Not Started
E | Failed signals + midtrend entries + (optional) pyramiding | Operationalise Schwager's most important rule and the high-value midtrend entries. | 12 failed-signal detectors, reversal wiring, four midtrend entries, pyramiding with guards. | F-040..F-043 green. In backtest on 5 tickers, failed-signal reversals improve net expectancy vs Phase-D baseline. | 3 | D | Not Started
F | Backtest / walk-forward harness | Validate the system honestly across multiple periods and markets with realistic costs. | backtest_harness, walk-forward split, slippage model, parameter-set sensitivity report, BacktestStudio UI. | Multi-period (3+) multi-market (5+) report with OOS expectancy, drawdown, win rate. No single 'optimum' relied on — variance across neighboring parameter sets reported. | 3 | E | Not Started
G | Discipline overlay (Ch 16-17) | Enforce the rules that make the system actually work in practice. | discipline_checks (plan-before-trade, no-averaging-down, stop-widening, streaks), DisciplineDashboard, 82-rules advisory engine. | Trader cannot save a stopless plan; averaging-down warned; drawdown-triggered size cut applied automatically; dashboard surfaces rule violations. | 2 | D | Not Started

## Book_Chapter_Map
Chapter | Title | Part | Core concepts (operational) | Decision rules (extract) | Computable artifacts (book code/) | Maps to pipeline stage(s)
3 | Trends | 1 — Basic tools | Uptrend/downtrend via HH/HL pivots; trend lines / TD lines / internal trend lines / channels; MAs as smoothed trend proxy. | Pullback entry on retest; trend-line penetration -> reversal alert; channel exceed -> profit-taking; MA cross alert. | 01_trend_pivots.py, 02_trend_lines.py, 03_td_lines.py, 04_internal_trend_line.py, 05_moving_average.py | s5_regime, s6L_direction, regime_inputs
4 | Trading ranges and S/R | 1 — Basic tools | Horizontal range bounded by S/R; concentration zones; envelopes (MA ± ATR); breakout termination of range. | Long at support / short at resistance with stop just past; breakout confirmation; range break failure -> bull/bear trap. | support_resistance.py, trading_range.py, concentration_zones.py, price_envelope.py, breakout.py | s5_regime, s6R_range, s7R_breakout, s9R_failed
5 | Chart patterns | 1 — Basic tools | Reversal (H&S, double top/bottom, rounding); continuation (flag, pennant, triangle); gaps; bar patterns (WRD, dojis). | Pattern completion -> measured-move target; pattern failure -> failed-signal reversal; pause-in-trend -> midtrend entry. | chart_patterns.py | s4_patterns, s10L_failed, s9R_failed, risk_targets
6 | Oscillators | 1 — Basic tools | Momentum, ROC, MA oscillator, MACD, RSI, Stochastics; divergence; overbought/oversold. | TREND: oscillators are alert-only; require price confirm. RANGE: actionable at boundaries (osc + S/R). | oscillators_master.py, generate_images.py | s3_indicators, osc_note (overlay)
7 | Is chart analysis still valid? | 1 — Basic tools | Confirmation layers (penetration, time delay, pattern, oscillator agree, fundamentals); multi-timeframe filter; failed-signal exploitation; risk-control asymmetry. | Need 2+ confirmations; short-term aligned with weekly/monthly; reverse on failed signal. | ch7_master.py | s9L_filter, s8R_confirm, s10L_failed
8 | Midtrend entry & pyramiding | 2 — Trading issues | % retracement (33/50/67); minor-reaction reversal; continuation breakout from flag; long-MA reaction. | Add to winners only when unrealised P&L positive; max 50% from pyramids; tighter stops on add; no-add after N consecutive losses. | 01_midtrend_entry.py, 02_percent_retracement.py, 03_reversal_minor_reaction.py, 04_continuation_breakout.py, 05_long_term_ma_reaction.py, 06_pyramiding.py | s7L_signal (midtrend), state_machine (pyramid loop)
9 | Stop-loss points | 2 — Trading issues | Stop-loss liquidation point set BEFORE entry; GTC orders; trend-line / range / pattern / WRD / relative-high-low / money / trailing stop. | Stop quality hierarchy: chart > swing > %/ATR > money. Stops never widen. Size = risk / (entry - stop). | 10 scripts: 01_stop_loss_liquidation_point.py .. 09_trailing_stop.py + 10_cic_anti_pattern.py | risk_stops
10 | Exit objectives | 2 — Trading issues | Chart-based / measured-move / S/R / RSI-extreme / contrary-opinion objectives; trailing stop; change-of-market-opinion exit. | Combine 2+ targets at same price -> high confidence; partial 50% at first target, trail the remainder. | (inferred from index — measured-move calc, S/R objective, trailing executor) | risk_targets
11 | Failed signals (THE rule) | 2 — Trading issues | 12 failure types: bull/bear traps, false TL break, filled gaps, return to spike/WRD extremes, counter-anticipated flag, opposite breakout, H&S target failure, double-top break, rounding break, reliability tag. | When pattern fails to deliver expected move -> reverse position; size smaller (still needs confirmation). | generate_illustrations.py, chapter11_demo.py, chapter11_detectors.py | s10L_failed, s9R_failed, failed_signal_principle
12 | Real-world chart analysis | 2 — Trading issues | 19 actual trades; 12 cross-cutting concepts (premise violation, stop quality, measured move, traps, flags, counter-anticipated, WRD, trailing, island/spike, expectancy). | Trade ends when premise is violated. Flexibility > prediction. Asymmetry near range extremes. | chapter12_concepts.py, generate_charts.py, wavelet_decomposer.py, emd_stl_decomposer.py, chart_decomposer.py | out_actions (illustrates every branch)
13 | Charting / analysis software | 3 — Trading systems | Data choices (historical / EOD / real-time); data cleaning; continuous futures rolls; software selection by timeframe. | EOD sufficient for swing/position; clean before backtest; never trust uncleaned data. | historical_price_data.py, end_of_day_data.py, real_time_data.py, software_selection.py, data_cleaning.py, continuous_futures.py | s2_data
14 | Trading systems: structure & design | 3 — Trading systems | Fast vs slow MA trade-off; MA / breakout systems; confirmation (penetration, time, pattern); filters; market-char adjustments; buy/sell asymmetry; pyramiding; trade exit; countertrend overlay; 3-level diversification. | Architecture template (8 steps); 10-point common-problems checklist. | 13 scripts: 01_trend_following_systems.py .. 13_diversification.py | s7L_signal, s9L_filter, s8R_confirm, state_machine
15 | Testing & optimising trading systems | 3 — Trading systems | Well-chosen-example fallacy; parameter sets; time stability; slippage; overfitting; in-sample vs out-of-sample; walk-forward; multi-market. | Optimize on train ONLY; evaluate on test; trade neighbors of optimum, not the optimum; test on 3+ markets. | 10 concept_*.py + 00_generate_illustrations.py | backtest_harness
16 | Planned trading approach | 4 — Practical guidelines | Seven-step blueprint (philosophy, markets, risk, planning routine, notebook, diary, analysis). Position sizing = risk / (entry-stop); volatility / equity / streak adjustments. | Risk per trade fixed before entry; reduce size after losing streak; segment trade analysis by direction / pattern / period. | 01_position_sizing.py, 02_volatility_sizing.py, 03_traders_notebook.py, 04_trade_analysis.py | risk_sizing, discipline, log_loop
17 | 82 trading rules | 4 — Practical guidelines | 82 rules across 7 sections: entries, exits/risk, money mgmt, holding winners, psychology, patterns, analysis/review. | Rule 76: failed signal more reliable than original. Cut losers, hold winners. Plan doesn't bend in bull/bear. Bad habits never cured, only latent. | 7 scripts: 01_entering_trades.py .. 07_analysis_review.py | discipline, all branches

## Risks_Open_Questions
ID | Category | Question / Risk | Why it matters | Assumed answer (for now) | Needed before phase | Status
Q-01 | Market scope | Are we targeting only Vietnamese stocks (HOSE/HNX/UPCOM) at first, or also crypto / US / futures? | Liquidity, data source, regime parameters and pattern detectors all differ. Schwager's examples are futures/equities. | DECIDED: VN equities only in v1 (HOSE/HNX/UPCOM via existing stock-data-service / vnstock). | B | Answered
Q-02 | Bar frequency | Daily bars only, or intraday too? | Real-time / tick data adds infra cost (Ch 13) and changes stop/target logic. | Daily bars only in v1. | B | Open
Q-03 | Action mode | Recommend only, paper trade, or eventually broker-integrated? | Compliance, security, and the discipline layer differ. Auto-execute is far higher risk. | DECIDED: Recommend-only in v1 (no execution, no broker). Paper-trade simulator may appear later via the Phase F backtest harness, but not as a v1 promise. | B | Answered
Q-04 | Universe size | How many tickers per user are we promising the helper supports per bar? | Drives caching strategy, batch size in orchestrator, and DB sizing. | Up to 30 tickers per user per bar in v1. | B | Open
Q-05 | Long-only or long/short? | Schwager treats both. VN cash equities are largely long-only retail. | Halves complexity if long-only; SHORT state in state-machine can be deferred. | DECIDED: Long + short both modelled. SHORT state shipped in v1. (Note: VN cash market doesn't allow true short — treat SHORT as 'short bias' / exit-then-wait recommendation, or paper-only.) | C | Answered
Q-06 | Account / risk-pref source | Where does account equity come from for sizing — user-typed, or portfolio-service valuation? | Sizing is meaningless without a real equity figure. | DECIDED: User-typed equity in v1 with manual override stored in user_risk_prefs. Portfolio-service valuation feed deferred to v2. | C | Answered
Q-07 | Authoritative pattern detector | Use book-Python scripts (knowledge/.../code/) directly, or re-implement inside services? | Reuse saves time but couples our service to research code style. | Re-implement inside ai-insights-service / decision-helper-service; book code as reference + test oracle. | A | Open
Q-08 | Multi-timeframe inputs | Do we require weekly + monthly bars for the multi-TF filter (Ch 7), or daily only? | Materially changes data access pattern and orchestrator cost. | Daily + weekly resampled from daily; no separate weekly fetch. | B | Open
Q-09 | Failed-signal sensitivity | Schwager's 12 detectors are sensitive to threshold tuning. Tune per-symbol, per-regime, or globally? | Per-symbol = more accurate but harder to validate; global = simpler. | Global defaults + per-user override; per-symbol learned in Phase F backtest. | E | Open
Q-10 | Execution price assumption | For backtest + paper-trade, do we use next-day open, close, or limit-at-signal? | Changes backtest results materially. | Next-day open in v1 (Schwager's typical assumption). | F | Open
Q-11 | Discipline enforcement strength | Does TradePlanModal HARD-block trades without stop+target, or just warn? | Hard-block = strongest discipline (Ch 17 spirit) but most friction. | DECIDED: Hard-block save when stop OR target is missing. Override flag exists but is recorded as a rule-violation in the journal. | D | Answered
Q-12 | Prediction-service overlay | Should ML predictions from prediction-service modify the recommendation, or stay advisory-only? | ML overlay can amplify signal but also overfit. Schwager-style discipline is the primary edge. | DECIDED: Advisory-only in v1. Surfaced in DecisionConsole sidebar; never used in stop / target / size / state transitions. | B | Answered
Q-13 | Localisation / language | Reason chain and discipline messages — English, Vietnamese, or both? | Frontend i18n footprint. | English in v1; Vietnamese in Phase G. | D | Open
Q-14 | Auth model for helper service | Reuse auth-service JWT, or new service-to-service token? | Consistency with the rest of the stack vs additional risk surface. | Reuse auth-service JWT (same as other services). | B | Open
Q-15 | Decision cadence | Run helper on every bar close, on user request, or both? | Continuous run -> infra cost; on-request -> stale data risk. | DECIDED: Daily scheduled run after market close for every watched ticker + on-demand recompute exposed via API (used by DecisionConsole 'Recompute now' button). | C | Answered